## Sheet1
DNS Management
Project Plan
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Outputs
Project Set Up
Project initiation
Project Budget
Draft LWBC
LWBC Endorsed | [12 empty] | LWBC
Project Kick off
Architecture
Technical requirements - F5
Technical requirements - Infoblox
Technical requirements - Cloud(s) Integration
Technical Requirements - DR | [12 empty] | Requirements gathered
Target State Architecture
Draft Architecture Council Paper
Present to AC for endorsement | [12 empty] | Architecture Confirmed
Design
Draft High Level Design | [12 empty] | High Level Design
Stakeholder Reviews
Ammendments
Detailed Design / As Built Documentation | [12 empty] | Detailed Design
Migration
High Level Technical Migration Plan
Stakeholder Reviews
Ammendments
Detailed Tech Migraton Plan | [12 empty] | Migration Plan
Build & Migrate
Deploy Pre Req Changes
Reconfigure Infoblox
Apply Cloud Integrations
Apply AD Integrations | [12 empty] | Build complete
Migrate F5
Migrate DR | [12 empty] | Migration Complete
Decommission
Decommission F5
Decommission DR
Clean up Tasks | [12 empty] | Decommission
Documentation
Update Operational Documentation
Update Support Documentation
Handover to BAU | [12 empty] | Platform handed over to BAU
FTE's
|  |  | Dec | Jan | Feb | Mar | Apr | May |  |  |  | Jun
Programme/Project mgr |  |  | 0.5 | 0.5 | 1 | 1 | 1 | 1 |  |  |  | 1
Technical PM | [5 empty] | 0.5 | 1 | 1 |  |  |  | 1
Architect |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  | 0.5
Senior Designer |  |  | 0.5 | 0.5 | 1 | 1 | 1 | 1 |  |  |  | 1
Technical BA |  |  |  | 0.25 | 0.5 | 1 | 1 | 1 |  |  |  | 1
Engineers
Vendors
Coordinator |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  | 1
Change manager |  |  |  |  | 0.5 | 0.5 | 1 | 1 |  |  |  | 1
Change Analyst |  |  |  |  | 0.5 | 0.5 | 1 | 1 |  |  |  | 1
Business Analyst |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  | 1
Contact Centre Snr management rep |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  | 1
Contact Centre Representative |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  | 1
Commercial rep
Procurrement
Communication rep | [6 empty] | 0.5 | 0.5 |  |  |  | 0.5
Sub Total |  |  | 1.5 | 1.75 | 8 | 9 | 11 | 11 |  |  |  | 11
Cost
| Rate | Monthly Cost | Dec | Jan | Feb | Mar | Apr | May |  |  |  | Jun
Programme/Project mgr | 182 | 30576 | 15288 | 15288 | 30576 | 30576 | 30576 | 30576 |  |  |  | 30576
Technical PM | 140 | 23520 | 0 | 0 | 0 | 11760 | 23520 | 23520 |  |  |  | 23520
Architect | 130 | 21840 | 10920 | 10920 | 10920 | 10920 | 10920 | 10920 |  |  |  | 10920
Senior Designer | 130 | 21840 | 10920 | 10920 | 21840 | 21840 | 21840 | 21840 |  |  |  | 21840
Technical BA | 130 | 21840 | 0 | 5460 | 10920 | 21840 | 21840 | 21840 |  |  |  | 21840
Engineers
Vendors
Coordinator | 100 | 16800 | 0 | 0 | 16800 | 16800 | 16800 | 16800 |  |  |  | 16800
Change manager | 130 | 21840 | 0 | 0 | 10920 | 10920 | 21840 | 21840 |  |  |  | 21840
Change Analyst | 110 | 18480 | 0 | 0 | 9240 | 9240 | 18480 | 18480 |  |  |  | 18480
Business Analyst | 130 | 21840 | 0 | 0 | 21840 | 21840 | 21840 | 21840 |  |  |  | 21840
Contact Centre Snr management rep | 110 | 18480 | 0 | 0 | 18480 | 18480 | 18480 | 18480 |  |  |  | 18480
Contact Centre Representative | 100 | 16800 | 0 | 0 | 16800 | 16800 | 16800 | 16800 |  |  |  | 16800
Commercial rep
Procurrement
Communication rep | 100 | 16800 | 0 | 0 | 0 | 0 | 8400 | 8400 |  |  |  | 8400
Sub Total |  |  | 37128 | 42588 | 168336 | 191016 | 231336 | 231336 |  |  |  | 231336
Cum Cost |  |  | 37128 | 79716 | 248052 | 439068 | 670404 | 901740 |  |  |  | 1133076

## Sheet2
Requirement
Option |  | Simplifies Management | Improves Supportability | Aligns with Strategy | Reduces Operational Cost
| Do Nothing | No | No | No | No
| Single Solution | Partial | Yes | Yes | Partial
| Cloud Only | Partial | Yes | Yes | Partial
| Hybrid | Yes | Yes | Yes | Yes